## 01. OE Team
OPERATIONS EXCELLENCE TEAM
Leader | Picture | Main Function | OE Function | Implementation tools |  |  | Responsible | Related area | Contact
Duy Phạm |  | Production Lead | OE Coordinator | OE Connection |  |  | Connect all Pillars to a dashboard of execution. Following activities of all pillars to call support ontime. | OE team | Email: duy.pham@ild-coffee.com Phone: +84384613654
Duy Phạm |  | Production Lead | AM Pillar Lead | Cleaning standard | Inspection standard | Centerline standard | Eliminate or reduce the forced failure to minimize the Operation performance loss. | Tipping Coffee processing Utility | Email: duy.pham@ild-coffee.com Phone: +84384613654
Dung Trần |  | Quality Manager | GA Pillar Lead | MOR/WOR/DOR/SHO | Measure cascading (KPI/PPI/API) |  | Ensure all OE' team activities are connected to business strategy and objectives, creating alignment and commitment across all levels | Whole factory | Email: dung.tran@ild-coffee.com Phone: +84975507180
Vũ Trần |  | R&D Lead | FI Pillar Lead | RCA DMAIC | IPA | KLL | Using the tools for data analysis & troubleshooting to improve equipment efficiency & optimize the costs. | Whole factory | Email: vu.tran@ild-coffee.com Phone: +84973846326
Bình Đặng |  | Food Safety Supervisor | Quality Pillar Lead | Q line mapping Microbiology | Q line mapping Foreinbody |  | Prevent defects at the source, maintain stable equipment and processes to achieve “Zero Defect,” and enhance customer satisfaction. | Coffee processing | Email: binh.dang@ild-coffee.com Phone: +84976667041
Thu Dương |  | HR Specilist | E&T Pillar Lead | Competency matrix | Multi-skilled Program |  | Manage & develop competency across the organization to ensure effective and sustainable OE implementation. | Whole factory | Email: thu.duong@ild-coffee.com Phone:+84985213615
Anh Trương |  | Maintenance Planning Supervisor | PM Pillar Lead | PM Master Plan | SOP/Tasklist management | Spare part management | Prevent breakdowns, optimize costs, and ensure long-term stable equipment performance through planned and predictive maintenance | Whole factory | Email: anh.truong@ild-coffee.com Phone: +84908566393
Hoàng Nguyễn |  | SHE Manager | SHE Pillar Lead | 5S Phase 2 | LOTO | CSD | Ensure safety, health, and environmental protection through standardized equipment, processes, and behaviors. Enhance 5S standard for the whole factory | Whole factory | Email: hoang.nguyen@ild-coffee.com Phone: +84329501881
Đức Mai |  | OPs Manager | OE Leader | All |  |  |  |  | Email: duc.mai@ild-coffee.com Phone: + 84975232032

## 01. Steering Committee (hidden)
| STRATEGY |  | GOAL ALIGNMENT |  | TPM
Role | Sponsor | OE Leader | OE Coordinator | GA Pillar Leader | TPM - SHE Pillar Leader | TPM - Q Pillar Leader | TPM - AM Pillar Leader | TPM - PM Pillar Leader | TPM - FI Pillar Leader | TPM - E&T Pillar Leader
Name | Thi Nguyen | Duc Mai | Duy Pham | Dung Tran | Hoang Nguyen | Dung Tran | Duy Pham | Anh Truong | Vu Tran | Thu Duong
Responsibility | Advise, Challenge, Strategy Decision maker, Motivation, Budget | Ensure methodology, alignment, timeline, effectiveness of all pillars. Key person to align strategy with GD | Connect all Pillars to a dashboard of execution. Following activities of all pillars to call support ontime. | On top of methodology. A person to decide the approach of methodology of this pillar to build the basic foudation of ILD | On top of methodology. Ensure safety, health, and environmental protection through standardized equipment, processes, and behaviors. Enhance 5S standard for the whole factory | On top of methodology. A person to decide the approach of methodology of this pillar to build quality methodology to ensure the good product for customer | On top of methodology. A person to decide the approach of methodology of this pillar to build the back bone of TPM to prevent the force deterioration of machine | On top of methodology. A person to decide the approach of methodology of this pillar to Preventive Maintenance to prevent the natural deterioration of machine | On top of methodology. A person to decide the approach of methodology of this pillar to build problem solving methodology for all pillars | On top of methodology. A person to decide the approach of methodology of this pillar to build training plan & ensure people competency

## 03. Attendance
OPERATIONS EXCELLANCE WEEKLY MEETING - ATTENDANCE TRACKING
No | Leader | Pillar | NOTE | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  |  | Sep |  | Oct |  | Nov |  | Dec |  | Punish | [8 empty] | 9
|  |  |  | Week 2 | Week 4 | Week 2 | Week 4 | Week 2 | Week 4 | Week 2 | Week 4 | Week 2 | Week 4 | Week 1 | Week 2 | Week 4 | Week 2 | Week 4 | Week 2 | Week 4 | Week 2 | Week 4 | Week 2 | Week 4 | Attendance | Action Plan | Milestone | Total | Fine paid | Remain | OE Team | date | set | count M | pay-ins | Q2 | Q3 | Q4
1 | Duc Mai | OE | Mandatory | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | [8 empty] | 100000 | 0 | 0 | 100000 | 100000 | 0 | Duc Mai | 2026-05-06 | 200000 | 6 | 1200000 | 600000 | 600000 | 0
2 | Duy Pham | AM/Coor. | Mandatory | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 0 | 10000 | 0 | 10000 | 10000 | 0 | Duy Pham | 2026-05-05 | 100000 | 6 | 600000 | 300000 | 300000 | 0
3 | Dung Tran | GA | Mandatory | 1 | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 3 | [8 empty] | 140000 | 10000 | 0 | 150000 | 80000 | 70000 | Dung Tran | 2026-05-08 | 200000 | 6 | 1200000 | 600000 | 600000 | 0
4 | Vu Tran | FI | Mandatory | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 0 | 10000 | 30000 | 40000 | 40000 | 0 | Vu Tran | 2026-05-08 | 100000 | 6 | 600000 | 300000 | 300000 | 0
5 | Nghia Bui | PM | Mandatory | 1 | 3 | 1 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | [8 empty] | 20000 | 0 | 10000 | 30000 | 20000 | 10000 | Nghia Bui | 2026-06-05 | 100000 | 6 | 600000 | 300000 | 300000 | 0
6 | Binh Dang | Q | Mandatory | 1 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | [8 empty] | 70000 | 0 | 0 | 70000 | 20000 | 50000 | Binh Dang | 2026-05-08 | 100000 | 6 | 600000 | 300000 | 300000 | 0
7 | Thu Duong | E&T | Mandatory | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | [8 empty] | 70000 | 0 | 20000 | 90000 | 10000 | 80000 | Thu Duong | 2026-05-06 | 100000 | 6 | 600000 | 300000 | 300000 | 0
8 | Hoang Nguyen | SHE | Mandatory | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | [8 empty] | 50000 | 0 | 20000 | 70000 | 20000 | 50000 | Hoang Nguyen | 2026-05-06 | 200000 | 6 | 1200000 | 600000 | 600000 | 0
9 | Yen Tran | Support E&T | Mandatory | 4 | 1 | 4 | 1 | 2 | 3 | 1 | 3 | 2 | [12 empty] | 140000 | 10000 | 0 | 150000 |  | 150000 | Yen Tran |  | 200000 | 0 | 0 | 0 | 0 | 0
10 | Thang Cao | Support PM | Mandatory | 4 | 4 | 4 | 4 | 2 | 1 | 2 | 1 | 2 | [12 empty] | 60000 | 0 | 0 | 60000 | 40000 | 20000 | Thang Cao | 2026-05-06 | 200000 | 3 | 600000 | 600000 | 0 | 0
[28 empty] | 560000 | 340000 | 260000 |  |  |  |  | 7200000
|  | 1 | Ontime
|  | 2 | Late
|  | 3 | Absent
|  | 4 | NA

## 04. Agenda
OE WEEKLY MEETING AGENDA
Time: 11:00 - 12:00 Every 2 weeks Duration: 60 minutes
| Content | Duration (min) | PIC
Plan | Review Action Plan | 10 | Duy Pham
KPI | Monthly review Factory KPI | 10 | Duy Pham | Review at the 1st meeting of the month
Plan | Review Master Plan & Milestones | 15 | Duy Pham
Project | Define next actions | 20 | All
Support | Escalation & Information | 15 | All

## 05. Master Planning
OPERATIONAL EXCELLENCE MASTER PLAN-2026 | [55 empty] | Week | 36
[56 empty] | 1 | Milestone
PILLAR | KEY ACTIVITIES | PIC | MEMBER | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May | [5 empty] | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | 2 | Done
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 3 | Late
GA-GOAL ALIGNMENT | Finalize GA Assessment Checklist | Dung Tran | Duc Mai | Mar 11: 2 | 0
| Finalize Department KPI/PPI/API | Dung Tran | Duc Mai | Mar 12: 2 | 0
| Regularly attend the Production/ENG/QA-Shift handover meeting (Sharing/Coaching/Recognizing) | Dung Tran | Duy Pham | Apr 15: 3; May 18: 2; Jul 29: 1; Jul 31: 2; Oct 42: 1 | 0
| Regularly attend the QA-WOR (Sharing/Coaching/Recognizing) | Vu Tran | Duy Pham | Apr 16: 3; May 18: 2; Jul 30: 3; Aug 32: 2; Oct 43: 1 | 10000
| Regularly attend the Engineering-WOR (Sharing/Coaching/Recognizing) | Dung Tran | Duc Mai | May 18: 2; Aug 32: 2; Nov 45: 1 | 0
| Regularly attend the OPs-WOR (Sharing/Coaching/Recognizing) | Dung Tran | Nghia Bui | Jun 23: 2; Sep 36: 1; Dec 49: 1 | 0
| Monthly meeting to Review Project 2026 | Duy Pham | All | Mar 11: 2; Apr 15: 2; May 20: 2; Jun 25: 2; Jul 29: 2; Aug 33: 2; Sep 38: 1; Oct 42: 1; Nov 46: 1; Dec 51: 1 | 0
AM-AUTONOMOUS MAINTENANCE | Finalize OE Final Assessment Checklist | Duy Pham | Duc Mai | Mar 11: 2 | 0
| FP&FD Working Group-OE Final Assessment | Duy Pham | OE team | Jun 26: 2 | 0
| ROA Working Group-OE Final Assessment | Duy Pham | OE team | Jul 29: 2 | 0
| EXT&EVAP Working Group-OE Final Assessment | Duy Pham | OE team | Aug 35: 2 | 0
| GRASSO Working Group-OE Final Assessment | Duy Pham | OE team | [52 empty] | 0 | bar: Sep 37
| BOILER Working Group-OE Final Assessment | Duy Pham | OE team | [52 empty] | 0 | bar: Oct 41
| WTP/WWTP Working Group-OE Final Assessment | Duy Pham | OE team | [52 empty] | 0 | bar: Nov 45
| TIP Working Group-OE Final Assessment | Duy Pham | OE team | [52 empty] | 0 | bar: Dec 49
FI-FOCUS IMPROVEMENT | Monthly Review RCA Effectiveness | Vu Tran | Duc Mai Dung Tran Duy Pham Nghia Bui | Feb 6: 2; Mar 10: 2; Apr 14: 2; May 18: 3; May 21: 2; Jun 24: 2; Jul 27: 2; Aug 32: 2; Sep 37: 1; Oct 41: 1; Nov 46: 1; Dec 50: 1 | 10000
| Monthly Tracking IPA (send monthly report) | Vu Tran | Vu Tran | Feb 5: 2; Mar 9: 2; Apr 13: 3; Apr 14: 3; Apr 15: 2; May 18: 2; Jun 24: 2; Jul 28: 3; Aug 33: 2; Sep 37: 1; Oct 41: 1; Nov 46: 1; Dec 50: 1 | 10000
| Implement DMAIC for FD | Vu Tran | Vu Tran | May 22: 2 | 0
E&T-EDUCATION & TRAINING | Finalize CM for Production | Thu Duong | Yen Tran | Mar 12: 3; Apr 13: 2 | 0
| Finalize CM for Engineering | Thu Duong | Yen Tran | Apr 14: 2 | 0
| Finalize CM for QA | Thu Duong | Yen Tran | Apr 14: 2 | 0
| Finalize CM for WH | Thu Duong | Yen Tran | Apr 14: 2 | 0
| Buildup Multi-skilled plan | Thu Duong | Yen Tran | Mar 12: 3; Apr 13: 2 | 0
| Monthly tracking Multi-skilled achievement | Thu Duong | Yen Tran | Apr 16: 2; May 21: 2; Jun 25: 3; Jun 26: 2; Jul 30: 3; Aug 34: 2; Sep 38: 1; Oct 43: 1; Nov 47: 1; Dec 51: 1 | 20000
QA-QUALITY ASSURANCE | Finalize Q-Line mapping for Microbiology | Binh Dang | Dung Tran | May 22: 2 | 0
| Monitor Q-Line mapping for Micro effectiveness | Binh Dang | Dung Tran | Jun 25: 2; Jul 30: 2; Aug 34: 2; Sep 39: 1; Oct 43: 1; Nov 47: 1; Dec 52: 1 | 0
| Finalize Q-Line mapping for Foreinbody | Binh Dang | Dung Tran | May 22: 2 | 0
| Monitor Q-Line mapping for FB effectiveness | Binh Dang | Dung Tran | Jun 25: 2; Jul 30: 2; Aug 34: 2; Sep 39: 1; Oct 43: 1; Nov 47: 1; Dec 52: 1 | 0
PLANNED MAINTENANCE | Complete PM Master Plan for Coffee Processing (Tipping to FP) | Nghia Bui | Thang Cao | May 22: 2 | 0
| Complete PM Master Plan for Utility and Facility | Nghia Bui | Thang Cao | May 22: 2 | 0
| Complete the Spare part list of Coffee Processing (Tipping to FP) | Nghia Bui | Thang Cao | May 21: 2 | 0
| Complete the Spare part list of Utility and Facility | Nghia Bui | Thang Cao | May 21: 2 | 0
| Complete Spare part Management System | Nghia Bui | Thang Cao | [52 empty] | 0 | bar: Oct 44
| List down M&I maintenance SOP and highlight the Critical SOP | Nghia Bui | Thang Cao | Aug 34: 2 | 0
| Complete the Critical SOP of M&I | Nghia Bui | Thang Cao | [52 empty] | 0 | bar: Dec 49
| List down E&A maintenance SOP and highlight the Critical SOP | Nghia Bui | Thang Cao | Aug 34: 3 | 10000
| Complete the Critical SOP of E&A | Nghia Bui | Thang Cao | [52 empty] | 0 | bar: Nov 48
| List down Utility and Facility maintenance SOP and highlight the Critical SOP | Nghia Bui | Thang Cao | Aug 34: 2 | 0
| Complete the Critical SOP of Utility and Facility | Nghia Bui | Thang Cao | [52 empty] | 0 | bar: Dec 50
SHE-SAFETY / HEALTH / ENVIRONMENT | ENG-Completed LOTO Mapping (Utility) | Hoang Nguyen | Hung Le | May 21: 3; Jun 24: 2 | 10000
| PRO-Review & Update LOTO Mapping | Hoang Nguyen | Vu Le | Apr 16: 2 | 0
| ENG-Completed LOTO Mapping (Maintenance) | Hoang Nguyen | Nam Truong | Apr 16: 2 | 0
| WH-Completed LOTO Mapping (Tipping) | Hoang Nguyen | Truong Tran | Jun 24: 21 | 0
| Review & Update LOTO Authorized for Production | Hoang Nguyen | Vu Le | May 17: 2 | 0
| Review & Update LOTO Authorized for Utility | Hoang Nguyen | Hung Le | May 22: 3; Jun 24: 2 | 10000
| Review & Update LOTO Authorized for Maintenance | Hoang Nguyen | Nam Truong | Jun 26: 2 | 0
| Review & Update LOTO Authorized for Tipping | Hoang Nguyen | Truong Tran | Jul 31: 2 | 0
| Completed 3S Standard for QA | Hoang Nguyen | Minh Thai | May 21: 2 | 0
| Completed 3S Standard for Production | Hoang Nguyen | Minh Thai | Jul 30: 2 | 0
| Completed 3S Standard for WH | Hoang Nguyen | Minh Thai | Jul 30: 2 | 0
| Completed 3S Standard Utility | Hoang Nguyen | Minh Thai | [52 empty] | 0 | bar: Sep 39
Note on Z22: Duy Pham: Training DMAIC

## 06. Action Plan
ACTION PLAN
No | Pillar | Action | PIC | Due Date | Status | Note | Punish
1 | PM | Cập nhật thêm Key activities cho PM (Utility / Facility) | Duy Pham | 2026-03-27 | Done | Done
2 | OE | Finalize master timeline | Duy Pham | 2026-03-27 | Done | Done
3 | PM | Finalize key activities of PM | Anh Truong | 2026-03-20 | Done | Book a Duc,c Dung,Duy,a Hoang,a Thang
4 | GA | Create Shift brief/SHO instruction & share to team | Dung Tran | 2026-03-20 | Done | Duc, Dung,Duy go together
5 | ET | Get training E&T (Competency matrix) | Thu Duong | 2026-03-20 | Done | Book meeting with Duy Pham - Done
6 | OE | Build Assessment checklist for all Pillar | Duy Pham | 2026-03-27 | Done | Done
7 | OE | Propose Award budget for certificated | Duy Pham | 2026-03-27 | Done | Done
8 | ET | Kick-off E&T to implementation | Thu Duong | 10-04-2026 16-Apr | Done | Thu collect E&T link with HODs-Done
9 | PM | Review timing of facility in PM Key activities | Anh Truong | 2026-04-10 | Done
10 | FI | FI book monthly meeting to review RCA effectiveness | Vu Tran | 2026-04-10 | Done
11 | Q | Adding measure to tracking NC | Duy Pham | 2026-03-27 | Done
12 | OE | Final the prizes & group to recognition | Duc Mai | 10-04-2026 16-Apr | Done | Total: 86tr/year
13 | GA | Create new measure & SHO instruction (Video instruction) | Dung Tran | 2026-04-17 | Done
14 | OE | Tìm cách monitor kết quả tại từng khu vực sau khi pass đánh giá | Duy Pham | 2026-04-25 | Done
15 | OE | Nominate project completed in Q1 & evaluation for recognition | Duy Pham | 2026-04-10 | Done | Done
16 | OE | Create reward list for factory & aligned | Duy Pham | 2026-04-17 | Done | Book meeting to final
17 | ET | Finalize CM of Production | Duy Pham | 2026-04-10 | Done | Done
18 | ET | Build Multi-skilled implementation plan | Thu Duong | 2026-04-10 | Done | Duy Support - Done
19 | ET | Finalize E&T key activities with chị Yến | Duy Pham | 10-04-2026 16-Apr | Done | Done
20 | FI | Sent IPA in Mar (detail % OPL/EPL,...) | Vu Tran | 2026-04-16 | Done
21 | PM | Book monthly meeting to review Work order | Anh Truong | 2026-04-16 | Done
22 | OE | Propose rules for OE meeting attendance | Duy Pham | 2026-04-16 | Done | Done
23 | OE | Discuss to increase nominal speed of FD (740 to 750 kg/hr) | Duc Mai | 2026-04-16 | Done | Done - Keep 740 kgs/h
24 | ET | Collect Multi skill plan & participant of all team | Yen Tran | 07-05-2026 13-May | Done | Pending Eng/PRO | 1
25 | ET | Collect form (assessment checklist, posttest,…) of multi skill program for all department | Thu Duong | 2026-05-15 | Done | Upload lên folder
26 | GA | Book session gemba WOR of Engineering | Dung Tran | 2026-05-08 | Done
27 | AM | Book re-assessment for FD/FP area | Duy Pham | 2026-05-08 | Done | Done
28 | PM | Final spare part management of FD | Anh Truong | 15-05-2026 31-May 12-Jun | Done |  | 2
29 | PM | Review work order in Quarter 1 & April (involve all relevant department) | Anh Truong | 29-04-2026 15-May | Done | Send invitation to all department Share link of WO progress
30 | PM | Completed PM of facility | Anh Truong | 02-05-2026 15-May | Done | Upload lên DMS
31 | GA | Book session gemba WOR of QA | Vu Tran | 2026-05-08 | Done
32 | GA | Finetune SHO instruction & apply for team | Duy Pham | 15-05-2026 25-May | Done | Done | 1
33 | PM | Completed Spare part management for EXT | Anh Truong | 2026-05-21 | Done
34 | FI | Monthly Review RCA Effectiveness in Apr | Vu Tran | 2026-05-15 | Done
35 | Q | Clarify expectation of Q line mapping | Binh Dang | 2026-05-15 | Done
36 | ET | Collect multi skilled achievement in Quarter 2 | Thu Duong | 21-06-2026 10-07 | Done
37 | Q | Complete Q Line mapping of Micro | Binh Dang | 2026-05-31 | Done
38 | Q | Complete Q Line mapping of FB | Binh Dang | 2026-05-31 | Done
39 | PM | Completed PM plan for GRA | Anh Truong | 2026-05-31 | Done
40 | SHE | ENG-Completed LOTO Mapping (Utility) | Hoang Nguyen | 31-05-2026 12-Jun | Done
41 | SHE | Review & Update LOTO Authorized for Utility | Hoang Nguyen | 31-05-2026 12-Jun | Done
42 | FI | Finalize third party for DMAIC implementation | Duc Mai | 2026-06-18 | Done
43 | PM | Completed Spare part management for EVAP | Anh Truong | 2026-06-12 | Done
44 | SHE | WH-Completed LOTO Mapping (Tipping) | Hoang Nguyen | 2026-06-12 | Done
45 | OE | Final OE assessment | Duc Mai | 2026-06-18 | Done
46 | FI | Book Problem solving evaluation session in Q2 | Vu Tran | 2026-06-30 | Done
47 | GA | Send Saving project recognition proposal in Q2 (get aligned with FC) | Duy Pham | 2026-07-05 | Done | Done
48 | QA | Send email monitoring result of FB | Binh Dang | 2026-06-20 | Done
49 | QA | Send email monitoring result of Micro | Binh Dang | 2026-06-20 | Done
50 | SHE | Review & Update LOTO Authorized for Maintenance | Hoang Nguyen | 2026-06-25 | Done
51 | ENG | Completed PM plan for BOI | Anh Truong | 02-07-2026 10-Jul | Done | Chưa official | 1
52 | ENG | Build Technical transfer program & Master plan | Duy Pham | 2026-07-03 | Done | Done
53 | GA | Book session attend SHO W29 | Dung Tran | 16-07-2026 24-Jul | Done |  | 1
54 | AM | Book meeting brainstorming to solve the dust in cold room | Duy Pham | 2026-07-10 | Done | Done 1.Completed reuse dust cold room project 2.Mua tools phá cà phê tích tụ trong cold room trong shutdown tháng 7
55 | AM | Book final assessment for Roasting area | Duy Pham | 2026-07-10 | Done | Done
56 | PM | Completed PM plan for WTP/WWTP | Nghia Bui | 2026-07-10 | Done
57 | PM | Completed Spare part management for FP | Nghia Bui | 2026-07-16 | Done | Pending approval
58 | GA | Regularly attend the QA-WOR | Vu Tran | 24-07-2026 14-Aug | Done |  | 1
59 | FI | Monthly Tracking IPA (send monthly report) in Jun | Vu Tran | 24-07-2026 14-Aug | Done
60 | Q | Monitor Q-Line mapping for Micro effectiveness | Binh Dang | 2026-07-24 | Done
61 | Q | Monitor Q-Line mapping for FB effectiveness | Binh Dang | 2026-07-24 | Done
62 | SHE | Completed 3S Standard for Production | Hoang Nguyen | 2026-07-24 | Done
63 | SHE | Completed 3S Standard for WH | Hoang Nguyen | 2026-07-24 | Done
64 | ET | Book monthly meeting to review Multi skilled | Thu Duong | 2026-08-07 | Cancel
65 | OE | Book meeting to discuss the AI digital application with IT | Duy Pham | 2026-08-14 | Done | Done
66 | GA | Regularly attend the Eng-WOR | Dung Tran | 2026-08-07 | Done
67 | FI | Monthly Tracking IPA (send monthly report) in Jul | Vu Tran | 2026-08-14 | Done
68 | PM | List down M&I maintenance SOP and highlight the Critical SOP | Nghia Bui | 2026-08-21 | Done
69 | PM | List down E&A maintenance SOP and highlight the Critical SOP | Nghia Bui | 21-08-2026 5-Sep | Late
70 | PM | List down Utility and Facility maintenance SOP and highlight the Critical SOP | Nghia Bui | 2026-08-21 | Done
71 | Q | Monitor Q-Line mapping for Micro effectiveness in Jul | Binh Dang | 2026-08-21 | Done
72 | Q | Monitor Q-Line mapping for FB effectiveness in Jul | Binh Dang | 2026-08-21 | Done
73 | PM | Build a master plan to complete critical SOP of Eng | Nghia Bui | 2026-09-10 | On going
74 | GA | Regularly attend the OPs-WOR (Sharing/Coaching/Recognizing) | Dung Tran | 2026-09-05 | On going
75 | FI | Monthly Review RCA Effectiveness | Vu Tran | 2026-09-10 | On going
76 | FI | Monthly Tracking IPA (send monthly report) | Vu Tran | 2026-09-10 | On going
77
78

## 7. KPI Measure
BUSINESS TARGET 2026
Target: 2.01
Target: 2.00
Target: < 1
Target: 0 case
Target: 0 case
YTD Target: 6 cases
Target: 0 case
Target: 100%

## KPI data tracking
BUSINESS TARGET 2026
PIC | Duc Mai |  | Duy Pham |  | Vu Tran |  | Vu Tran |  | Yen Tran |  | Hoang Nguyen |  | Dung Tran |  | Dung Tran |  | Hoang Nguyen |  | Dung Tran |  | Dung Tran
KPI | CONVERTED VOLUME |  | RW GENERATION |  | YIELD OF VG2 |  | YIELD OF CONILON |  | TURN-OVER |  | LTI |  | MAJOR COMPLAINT |  | OTHER COMPLAINT |  | MAJOR FINDING |  | CERT. RENEWAL |  | TOTAL NC
Month | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Top Defect
Jan | 478987.2 | 487541.5556 | 4000 | 1040 | 2.01 | 2.01 | 2 | 2.01 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 100% | 100% | 20000 | 25044 | 1. Micro: 14040 2. Organic: 3978 3. Out sensory: 1038
Feb | 429436.8 | 468406 | 4000 | 380 | 2.01 | 1.99 | 2 | 2.01 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0 | 0 | 100% | 100% | 20000 | 10508
Mar | 396403.2 | 426380 | 4000 | 0 | 2.01 | 1.99 | 2 | NA | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0 | 0 | 100% | 100% | 20000 | 8358
Apr | 462470.4 | 477410 | 4000 | 0 | 2.01 | 2 | 2 | NA | 0.8 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 100% | 100% | 20000 | 7120
May | 478987.2 | 492932 | 4000 | 1420 | 2.01 | 2 | 2 | NA | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 100% | 100% | 20000 | 10695
Jun | 462470.4 | 491563 | 4000 | 300 | 2.01 | 1.99 | 2 | NA | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 100% | 100% | 20000 | 10652
Jul | 478987.2 | 509266 | 4000 | 350 | 2.01 | 1.99 | 2 | NA | 0.8 | 1 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0 | 0 | 100% | 100% | 20000 | 2510
Aug | 478987.2 |  | 4000 |  | 2.01 |  | 2 |  | 0.8 |  | 0 |  | 0 |  | 0.5 |  | 0 |  | 100% |  | 20000
Sep | 462470.4 |  | 4000 |  | 2.01 |  | 2 |  | 0.8 |  | 0 |  | 0 |  | 0.5 |  | 0 |  | 100% |  | 20000
Oct | 478987.2 |  | 4000 |  | 2.01 |  | 2 |  | 0.8 |  | 0 |  | 0 |  | 0.5 |  | 0 |  | 100% |  | 20000
Nov | 462470.4 |  | 4000 |  | 2.01 |  | 2 |  | 0.8 |  | 0 |  | 0 |  | 0.5 |  | 0 |  | 100% |  | 20000
Dec | 478987.2 |  | 4000 |  | 2.01 |  | 2 |  | 0.8 |  | 0 |  | 0 |  | 0.5 |  | 0 |  | 100% |  | 20000
YTD | 5549644.8 | 3353498.5556 | 48000 | 3490 | 2.01 | 1.9957 | 2 | 2.01 | 9.6 | 2 | 0 | 0 | 0 | 0 | 6 | 3 | 0 | 0 | 100% | 100% | 240000 | 74887

## OE meeting rules
OE MEETING RULES |  |  |  | OE Team Fund Tracking
No | VIOLATE | RULE | NOTE | task | date | Contribute | payment
1 | Tham gia meeting trễ giờ | 20000 | Trễ 1' sau khi start meeting | Budget | 2026-04-24 | 7200000 | 0
2 | Không tham gia meeting | 50000 | Không chấp nhận lí do | Fine paid | 2026-05-08 | 340000 | 0
3 | Trễ action/Milestone | 10000 | 1 lần | Fruit | 2026-05-08 |  | -179000
|  |  |  | Fruit | 2026-05-22 |  | -200000
QUỸ OE: 100k/member/tháng . Manager: 200k/tháng |  |  |  | 1st Engagement lunch in Quarter 2 | 2026-05-22 |  | -1683000
1 | Chuẩn bị trái cây cho meeting | 2 lần/tháng | Thu Duong | Fruit | 2026-06-05 |  | -100000
2 | OE team engagement | 2 lần/quý | Duy Pham | 2nd Engagement lunch in Quarter 2 | 2026-06-19 |  | -1824000
Tiền phạt sẽ xung công để phục vụ cho team. Thu quỹ bắt đầu từ tháng 4 |  |  |  | 1st Engagement lunch in Quarter 3 | 2026-08-03 |  | -1954000
Thủ Qũy: Thu Duong |  |  |  | Fruit | 2026-08-14 |  | -217154
[5 empty] | Total | 7540000 | -6157154
[6 empty] | Remain | 1382846

## Engagement plan
2026-OE TEAM ENGAGEMENT PLAN |  |  |  | 2nd Engagement lunch in Quarter 3 - 11/9
No | Activity | Time | Status | No. | Menu | Prize | Qyt | Total
1 | 1st Engagement lunch in Quarter 2 | May | Done | 1 | Cơm chiên trùm trứng | 57000 | 2 | 114000
2 | 2nd Engagement lunch in Quarter 2 | Jun | Done | 2 | Đuôi heo chiên giòn | 127000 | 2 | 254000
3 | 1st Engagement lunch in Quarter 3 | Jul | Done | 3 | Rau luộc kho quẹt | 67000 | 2 | 134000
4 | 2nd Engagement lunch in Quarter 3 | Sep |  | 4 | Cá diêu hồng chiên xù bánh tráng + rau | 197000 | 2 | 394000
5 | 1st Engagement lunch in Quarter 4 | Oct |  | 5 | Lẩu thái | 247000 | 2 | 494000
6 | 2nd Engagement lunch in Quarter 4 | Dec |  | 6 | Tráng miệng | 30000 | 2 | 60000
|  |  |  | 7 | Nước | 15000 | 12 | 180000
1630000